## Work Breakdown Structure
Project Name
Sample Work Breakdown Structure
Note: The work items below should be further broken down.
Project 0.0
Planning and Project Management 1.0 | Analysis 2.0 | Design 3.0 | Build 4.0 | Test 5.0 | Deploy 6.0 | Close 7.0
1.1 Workplan Creation | 2.1 As-Is Process Flows | 3.1 Functional Design | 4.1 Web Components | 5.1 Test Strategy | 6.1 Training | 7.1 Lessons Learned
1.2 Change Mgmt Plan | 2.2 To-Be Process Flows | 3.2 Technical Design | 4.2 Software Components | 5.2 Test Approach | 6.2 Security Setup | 7.2 Post Implementation Report
1.3 Issue Mgmt Plan | 2.3 Fit Gap | 3.3 Usability Prototype | 4.3 Hardware Components | 5.3 Test Conditions | 6.3 Deployment Planning | 7.3 Closeout
1.4 Risk Mgmt Plan | 2.4 Business Process Inventory | 3.4 Configuration Design | 4.4 Unit Test Plans | 5.4 Test Scope | 6.4 Deployment
1.5 Scope Mgmt Plan | 2.5 DR Plan Requriements | 3.5 DR Architecture Design | 4.5 Create DR Plan | 5.5 Test Execution
1.6 Communications Mgmt Plan |  |  |  | 5.6 Test DR Plan
1.7 Procurement Mgmt Plan
2012-05-17
Version 2, 5/17/2012
The University of Minnesota is an equal opportunity educator and employer. This publication/material is available in alternative formats upon request. Direct requests to oca@umn.edu. Printed on recycled and recyclable paper with at least 10 percent postconsumer material. ©2012 Regents of the University of Minnesota. All rights reserved.